## NZ
Network Zone
Week Of | Activities | Owners | Downtime | Comments
2017-04-30 | NZ bib file, LR extract (SFX transformed to LR xlsx file), and fiscal period information due on ExL FTP server by 5/6/2017 | all
2017-05-07 | Migration activities | ExL Migration
2017-05-14 | Migration activities | ExL Migration
2017-05-21 | Migration activities | ExL Migration
2017-05-28 | ExL Project Team checks migrated data | ExL PS
2017-06-04 | ExL Project Team delivers cutover environment; CO+WG check data; data publishing to Primo is started; CSU confirms acceptance of Alma data migration; NZ GO LIVE IS 6/7/2017 | all

## San Marcos + Sac State
Sacramento State, San Marcos
Dates | Days | Activities | Owners | Downtime
2017-06-06 | Tuesday | Campuses notify ExL when ready to freeze Alma and begin using offline circ | all | Alma full freeze begins
2017-06-07 | Wednesday | Migration begins activities; Alma offline circ continues | ExL Migration
2017-06-08 | Thursday | Migration completes activities; ExL Project Team checks migrated environment and delivers to customers; Alma offline circ continues | ExL PS
2017-06-09 | Friday | campuses + CO check environments; data publishing to Primo begins; CSU confirms acceptance of moved Alma; Alma offline circ continues | all | Primo config freeze begins
2017-06-10 | Saturday | data publishing to Primo continues; Alma offline circ continues | all
2017-06-11 | Sunday | Primo publishing completes; ExL Project Team checks and delivers Alma & Primo to CSU and campuses; Alma offline circ continues | all
2017-06-12 | Monday | CSU and campuses check Primo and confirms acceptance; ExL turns on job schedule; Alma offline circ files loaded when campuses are ready to end freeze | all | Alma full freeze ends; Primo config freeze ends
2017-06-13 | Tuesday | GO-LIVE DATE IS 6/13; live work resumes on Alma and Primo

## Group 1
Group 1: East Bay, Humboldt (Voy), Chico, Bakersfield (Voy), Dominguez Hills, Northridge, Fresno
Week Of | Activities | Owners | Downtime | Comments
2017-04-02 | CSU updates Alma Health Checklist on Basecamp; CSU begins prep of Migration Form, Field Mapping Form (III), P2E, 360 Forms, Delivered Files List; ExL Project Team answers questions and assists with checklist issues | all | n/a
2017-04-09 | CSU continues prep of Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List; ExL sending feedback & answering questions from forms and health checklist | all | n/a
2017-04-16 | DRAFT Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List posted to SF case for ExL Project & Migration Teams review | all | n/a
2017-04-23 | Final revisions to Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List updated to SF case; ExL sending feedback & answering questions | all
2017-04-30 | FINAL Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List due via SF cases for Migration Team Review | all
2017-05-07 | Data files due on ExL FTP server by end of week | all | III + Voy tech freeze (no further Cat + Acq); Alma config freeze begins
2017-05-14 | Migration activities | ExL Migration
2017-05-21 | Migration activities | ExL Migration
2017-05-28 | ExL Project Team checks migrated data | ExL PS
2017-06-04 | ExL Project Team delivers cutover environment; campuses + CO check data; data publishing to Primo is started; CSU confirms acceptance of Alma data migration; CSU delivers final fulfillment data (loans, patrons, requests) | all | Primo config freeze begins; Alma config freeze ends
2017-06-11 | Primo publishing completes; ExL Migration loads fulfillment data; ExL Project Team checks and delivers Alma & Primo to CSU; CSU checks fulfillment data & Primo and confirms acceptance; ExL turns on job schedule and unscrubs e-mail; GO LIVE DATE IS 6/13 -- each campus notifies CSU and ExL when live work has begun | all | III + Voy circ freeze (no further activity in III, Voy, or 360; use Alma Offline Circ - 2 days); Primo config freeze ends
2017-06-18 | CSU updates Alma Health Checklist; ExL Project Team answers questions and assists with checklist issues | all
2017-06-25 | Planning for Switch To Support (est 7/31) | all

## Group 2
Group 2: Monterey Bay (Voy), Sonoma, Maritime, Fullerton, Channel Islands (Voy), Los Angeles, Long Beach, Pomona
Week Of | Activities | Owners | Downtime | Comments
2017-04-09 | CSU updates Alma Health Checklist on Basecamp; CSU begins prep of Migration Form, Field Mapping Form (III), P2E, 360 Forms, Delivered Files List; ExL Project Team answers questions and assists with checklist issues | all | n/a
2017-04-16 | CSU continues prep of Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List; ExL sending feedback & answering questions from forms and health checklist | all | n/a
2017-04-23 | DRAFT Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List posted to SF case for ExL Project & Migration Teams review | all | n/a
2017-04-30 | Final revisions to Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List updated to SF case; ExL sending feedback & answering questions | all
2017-05-07 | FINAL Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List due via SF cases for Migration Team Review | all
2017-05-14 | Data files due on ExL FTP server by end of week | all | III + Voy tech freeze (no further Cat + Acq); Alma config freeze begins
2017-05-21 | Migration activities | ExL Migration
2017-05-28 | Migration activities | ExL Migration
2017-06-04 | ExL Project Team checks migrated data | ExL PS
2017-06-11 | ExL Project Team delivers cutover environment; campuses + CO check data; data publishing to Primo is started; CSU confirms acceptance of Alma data migration; CSU delivers final fulfillment data (loans, patrons, requests) | all | Primo config freeze begins; Alma config freeze ends
2017-06-18 | Primo publishing completes; ExL Migration loads fulfillment data; ExL Project Team checks and delivers Alma & Primo to CSU; CSU checks fulfillment data & Primo and confirms acceptance; ExL turns on job schedule and unscrubs e-mail; GO LIVE DATE IS 6/20 -- each campus notifies CSU and ExL when live work has begun | all | III + Voy circ freeze (no further activity in III, Voy, or 360; use Alma Offline Circ - 2 days); Primo config freeze ends
2017-06-25 | CSU updates Alma Health Checklist; ExL Project Team answers questions and assists with checklist issues | all
2017-07-02 | Planning for Switch To Support (est 7/31) | all

## Group 3
Group 3: San Jose, Stanislaus, San Bernardino, San Luis Obispo, Moss Landing, San Diego, San Francisco
Week Of | Activities | Owners | Downtime | Comments
2017-04-16 | CSU updates Alma Health Checklist on Basecamp; CSU begins prep of Migration Form, Field Mapping Form (III), P2E, 360 Forms, Delivered Files List; ExL Project Team answers questions and assists with checklist issues | all | n/a
2017-04-23 | CSU continues prep of Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List; ExL sending feedback & answering questions from forms and health checklist | all | n/a
2017-04-30 | DRAFT Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List posted to SF case for ExL Project & Migration Teams review | all | n/a
2017-05-07 | Final revisions to Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List updated to SF case; ExL sending feedback & answering questions | all
2017-05-14 | FINAL Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List due via SF cases for Migration Team Review | all
2017-05-21 | Data files due on ExL FTP server by end of week | all | III + Voy tech freeze (no further Cat + Acq); Alma config freeze begins
2017-05-28 | Migration activities | ExL Migration
2017-06-04 | Migration activities | ExL Migration
2017-06-11 | ExL Project Team checks migrated data | ExL PS
2017-06-18 | ExL Project Team delivers cutover environment; campuses + CO check data; data publishing to Primo is started; CSU confirms acceptance of Alma data migration; CSU delivers final fulfillment data (loans, patrons, requests) | all | Primo config freeze begins; Alma config freeze ends
2017-06-25 | Primo publishing completes; ExL Migration loads fulfillment data; ExL Project Team checks and delivers Alma & Primo to CSU; CSU checks fulfillment data & Primo and confirms acceptance; ExL turns on job schedule and unscrubs e-mail; GO LIVE DATE IS 6/27 -- each campus notifies CSU and ExL when live work has begun | all | III + Voy circ freeze (no further activity in III, Voy, or 360; use Alma Offline Circ - 2 days); Primo config freeze ends
2017-07-02 | CSU updates Alma Health Checklist; ExL Project Team answers questions and assists with checklist issues | all
2017-07-09 | Planning for Switch To Support (est 7/31) | all