## Network Zone
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Non-EXL ILS Alma Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 0% | Provide updated migration inputs to ExL project team – ExL project team will update CRM with: 1. Final Migration form (green valid cover page) 2. Final Mapped fields (green valid cover page) 3. Draft eResources P2E (final P2E provided/used in step 2.1.9) 4. Draft Delivered files Excel list indicating the files provided and their attributes | 1 day | 2017-04-22 | 2017-04-22 | 2 weeks prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer
| 1.1.2 | 0% | Customer ensure all libraries, locations and vendors in their ILS (and ERM system, if relevant) are reflected in Alma with the same codes in prep for cutover. | 1 day | 2017-05-06 | 2017-05-06 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1 | 0% | Technical Freeze and Extract/Transform
| 2.1.1 | 0% | ILS backups done | 2 hours | 2017-05-06 19:00 | 2017-05-06 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-07 02:00 | 2017-05-07 04:00
| 2.1.2 | 0% | Link Resolver (and ERM system, if relevant) backups done | 2 hours | 2017-05-06 19:00 | 2017-05-06 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-07 02:00 | 2017-05-07 04:00
MigOps | 2.1.3 | 0% | Freeze config changes on Alma PROD Configuration on Alma should not be done again until data has been reviewed and accepted in step 3.1.8 | 0 days | 2017-05-06 21:30 | 2017-05-06 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer/ExL Imp. |  | 2017-05-07 04:30 | 2017-05-07 04:30
| 2.1.4 | 0% | Export Customer institution from PROD to IMPL | 1 day | 2017-05-07 | 2017-05-07 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.5 | 0% | Freeze Technical services in ILS, LR (and ERM, if necessary). (Tech services= everything other than loans, requests and patrons/fines which will continue to be up and running until the fulfillment cutover below). Circulation activity continues (Patrons/fines, loans, requests). | 0 days | 2017-05-06 23:30 | 2017-05-06 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-07 06:30 | 2017-05-07 06:30
| 2.1.6 | 0% | Perform ILS full extract of all data in scope, as contracted with ExL and delivered at test load. | 10 hours | 2017-05-06 23:30 | 2017-05-06 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.7 | 0% | Perform Link Resolver full extract | 5 hours | 2017-05-06 23:30 | 2017-05-06 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.8 | 0% | Perform ERM full extract, if necessary | 5 hours | 2017-05-06 23:30 | 2017-05-06 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.9 | 0% | Upload ILS data to ExL S/FTP along with: 1. Final eResources P2E file 2. Final Delivered files Excel list indicating the files provided and their attributes | 5 hours | 2017-05-06 23:30 | 2017-05-06 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-07 06:30 | 2017-05-07 06:30
MigOps | 2.1.10 | 0% | Send confirmation to EXL that data is ready to download. | 0 days | 2017-05-06 23:30 | 2017-05-06 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-07 06:30 | 2017-05-07 06:30
| 2.1.11 | 0% | ILS data extract transfer to cloud | 1 day | 2017-05-07 | 2017-05-07 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.12 | 0% | Link Resolver data extract transfer to cloud | 1 day | 2017-05-07 | 2017-05-07 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.13 | 0% | ERM data extract transfer to cloud, if necessary | 1 day | 2017-05-07 | 2017-05-07 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.14 | 0% | Contact all electronic data suppliers with a request to use Primo service page as a link resolver instead of SFX. Must be effective from Primo go-live date | 0 days | 2017-05-06 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1 | 0% | Data load and processing activities
MigOps | 3.1.1 | 0% | Full data transform and load to IMPL | 5 days baseline (Add .5 day for each 1M records) | 2017-05-07 | 2017-06-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | Data released on IMPL for ExL Imp. quick checks of migrated data | 4 hours | 2017-06-01 | 2017-06-04 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration / ExL Imp. |  | 2017-06-01 07:00 | 2017-06-04 07:00
MigOps | 3.1.3 | 0% | Copy clean data back to PROD | 10 hours | 2017-06-05 | 2017-06-05 10:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-05 07:00 | 2017-06-05 17:00
| 3.1.7 | 0% | Customer data testing of clean data on Prod | 2 days | 2017-06-05 | 2017-06-07 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1.8 | 0% | Milestone: Customer data acceptance | 0 days | 2017-06-07 17:00 | 2017-06-07 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Fulfillment cutover activities
| 4.1.1 | 0% | Final ILS backup | 2 hours | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | #VALUE! | #VALUE!
| 4.1.2 | 0% | Perform final ILS extract of patrons, loans and requests. | 2 hours | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | #VALUE! | #VALUE!
| 4.1.3 | 0% | Send confirmation to EXL that fufillment data (patrons, loans and requests) are ready for download | 0 days | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | #VALUE! | #VALUE!
| 4.1.4 | 0% | Set Primo (and ILS OPAC, if relevant) to read-only | 0 days | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 4.1.5 | 0% | Transform and load patrons, loans and requests to Alma | 1 day | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | #VALUE! | #VALUE!
| 4.1.7 | 0% | Use Alma offline circ | 2 days | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer | Need Customer to install Alma offline circ client on fulfillment machines beforehand and test
| 4.1.6 | 0% | Customer data testing of clean patron, loan and request data on Prod | 4 hours | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.8 | 0% | Provide offline circ transactions file | 0 days | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.9 | 0% | Load offline circulation transactions file into Alma | 1 hour | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.10 | 0% | Customer test offline transactions in Alma | 1 hour | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.11 | 0% | Finalize all batch jobs scheduling | 0 days | 2017-06-05 17:00 | 2017-06-05 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.12 | 0% | Milestone: Customer Accept Alma environment | 0 days | 2017-06-05 18:00 | 2017-06-05 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1 | 0% | Primo-Alma integration
| 5.1.1 | 0% | Follow internal STP cloud request steps for Primo | 0 days | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp. | Internal -Documentation Center / General / Company Procedures / Professional Services
| 5.1.2 | 0% | Cloud checks/confirms that STP steps were implemented | 5 days | 2017-05-15 | 2017-05-22 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.3 | 0% | Re-Add Primo S/FTP address to Alma's S/FTP include list and run full Primo publish from Alma | 1/2 day | 2017-06-05 | 2017-06-05 | 3.1.3 | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.4 | 0% | Extract availability file from Alma for Primo Central | 1/2 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.5 | 0% | Load Alma data into Primo & Indexing | 1 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.6 | 0% | Load data from other Customer data sources, if necessary. | 1 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.7 | 0% | Verify Primo with full clean data re-published. | 1 day | 2017-06-04 08:00 | 2017-06-04 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1.8 | 0% | Activate ongoing publishing | 0 days | 2017-06-04 | 2017-06-04 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.9 | 0% | Milestone: Customer Accept Primo-Alma environment | 0 days | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1 | 0% | Go-Live Milestones
| 6.1.1 | 0% | Ensure relevant jobs are enabled/disabled in preparation for go-live process | 0 days | 2017-06-06 | 2017-06-06 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 6.1.2 | 0% | Go-Live Process Run/Enabled: 1. Removes 'SCRUBBED_' from all patron and vendor emails. 2. Remove all email and ftp include list entries 3. Enable preferred term correction capability (disable_preferred_term_correction_job=false) 4. Unhide configuration (hide_configuration=false) presuming certification has been completed. 5. Enable scheduled jobs (enable_scheduled_jobs=true) | 1 hour | 2017-06-06 | 2017-06-06 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | ExL Imp. Updates case with Unscrub request
| 6.1.3 | 0% | Go-Live with Alma | 0 days | 2017-06-06 | 2017-06-06 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.4 | 0% | Go-Live with Primo-Alma | 0 days | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.5 | 0% | All OpenURL compliant data sources point to Primo service page | 0 days | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.6 | 0% | Complete any relevant data publish to external parties, if relevant (OCLC, Libraries Australia, COPAC, SunCat, HathiTrust, Google Scholar, among others) | .5 day | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.7 | 0% | Complete any load of local Authority records, if relevant. | .5 day | n/a | n/a |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.8 | 0% | Switch Customer Alma status to 'Live PS' in CRM | 0 days | 2017-06-06 | 2017-06-06 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
Formulas:
Internal Use: HQ ST = Table139[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)
Internal Use: HQ FT = Table139[[#This Row],[Finish Date/ Time (Local Cust Time)]]+(O1/24)
Note on E10: Fixed duration
Note on E17: Fixed duration
Note on E18: Fixed duration
Note on E19: Fixed duration
Note on E23: Fixed duration
Note on E24: Fixed duration

## Group 1 Innovative
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Non-EXL ILS Alma Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 0% | Provide updated migration inputs to ExL project team – ExL project team will update CRM with: 1. Final Migration form (green valid cover page) 2. Final Mapped fields (green valid cover page) 3. Draft eResources P2E (final P2E provided/used in step 2.1.9) 4. Draft Delivered files Excel list indicating the files provided and their attributes | 1 day | 2017-05-01 | 2017-05-01 | 2 weeks prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer
| 1.1.2 | 0% | Customer ensure all libraries, locations and vendors in their ILS (and ERM system, if relevant) are reflected in Alma with the same codes in prep for cutover. | 1 day | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1 | 0% | Technical Freeze and Extract/Transform
| 2.1.1 | 0% | ILS backups done | 2 hours | 2017-05-13 19:00 | 2017-05-13 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 02:00 | 2017-05-14 04:00
| 2.1.2 | 0% | Link Resolver (and ERM system, if relevant) backups done | 2 hours | 2017-05-13 19:00 | 2017-05-13 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 02:00 | 2017-05-14 04:00
MigOps | 2.1.3 | 0% | Freeze config changes on Alma PROD Configuration on Alma should not be done again until data has been reviewed and accepted in step 3.1.8 | 0 days | 2017-05-13 21:30 | 2017-05-13 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer/ExL Imp. |  | 2017-05-14 04:30 | 2017-05-14 04:30
| 2.1.4 | 0% | Export Customer institution from PROD to IMPL | 1 day | 2017-05-14 | 2017-05-14 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.5 | 0% | Freeze Technical services in ILS, LR (and ERM, if necessary). (Tech services= everything other than loans, requests and patrons/fines which will continue to be up and running until the fulfillment cutover below). Circulation activity continues (Patrons/fines, loans, requests). | 0 days | 2017-05-13 23:30 | 2017-05-13 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 06:30 | 2017-05-14 06:30
| 2.1.6 | 0% | Perform ILS full extract of all data in scope, as contracted with ExL and delivered at test load. | 10 hours | 2017-05-13 23:30 | 2017-05-13 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.7 | 0% | Perform Link Resolver full extract | 5 hours | 2017-05-13 23:30 | 2017-05-13 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.8 | 0% | Perform ERM full extract, if necessary | 5 hours | 2017-05-13 23:30 | 2017-05-13 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.9 | 0% | Upload ILS data to ExL S/FTP along with: 1. Final eResources P2E file 2. Final Delivered files Excel list indicating the files provided and their attributes | 5 hours | 2017-05-13 23:30 | 2017-05-13 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 06:30 | 2017-05-14 06:30
MigOps | 2.1.10 | 0% | Send confirmation to EXL that data is ready to download. | 0 days | 2017-05-13 23:30 | 2017-05-13 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 06:30 | 2017-05-14 06:30
| 2.1.11 | 0% | ILS data extract transfer to cloud | 1 day | 2017-05-14 | 2017-05-14 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.12 | 0% | Link Resolver data extract transfer to cloud | 1 day | 2017-05-14 | 2017-05-14 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.13 | 0% | ERM data extract transfer to cloud, if necessary | 1 day | 2017-05-14 | 2017-05-14 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.14 | 0% | Contact all electronic data suppliers with a request to use Primo service page as a link resolver instead of SFX. Must be effective from Primo go-live date | 0 days | 2017-05-13 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1 | 0% | Data load and processing activities
MigOps | 3.1.1 | 0% | Full data transform and load to IMPL | 5 days baseline (Add .5 day for each 1M records) | 2017-05-14 | 2017-06-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | Data released on IMPL for ExL Imp. quick checks of migrated data | 4 hours | 2017-06-01 | 2017-06-04 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration / ExL Imp. |  | 2017-06-01 07:00 | 2017-06-04 07:00
MigOps | 3.1.3 | 0% | Copy clean data back to PROD | 10 hours | 2017-06-05 | 2017-06-05 10:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-05 07:00 | 2017-06-05 17:00
| 3.1.7 | 0% | Customer data testing of clean data on Prod | 2 days | 2017-06-05 | 2017-06-07 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1.8 | 0% | Milestone: Customer data acceptance | 0 days | 2017-06-07 17:00 | 2017-06-07 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Fulfillment cutover activities
| 4.1.1 | 0% | Final ILS backup | 2 hours | 2017-06-11 20:00 | 2017-06-11 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-12 03:00 | 2017-06-12 05:00
| 4.1.2 | 0% | Perform final ILS extract of patrons, loans and requests. | 2 hours | 2017-06-11 20:00 | 2017-06-11 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-12 03:00 | 2017-06-12 05:00
| 4.1.3 | 0% | Send confirmation to EXL that fufillment data (patrons, loans and requests) are ready for download | 0 days | 2017-06-11 22:00 | 2017-06-11 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-12 05:00 | 2017-06-12 05:00
| 4.1.4 | 0% | Set Primo (and ILS OPAC, if relevant) to read-only | 0 days | 2017-06-11 22:00 | 2017-06-11 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 4.1.5 | 0% | Transform and load patrons, loans and requests to Alma | 1 day | 2017-06-11 22:30 | 2017-06-11 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-12 05:30 | 2017-06-12 05:30
| 4.1.7 | 0% | Use Alma offline circ | 2 days | 2017-06-11 20:00 | 2017-06-13 08:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer | Need Customer to install Alma offline circ client on fulfillment machines beforehand and test
| 4.1.6 | 0% | Customer data testing of clean patron, loan and request data on Prod | 4 hours | 2017-06-11 10:00 | 2017-06-11 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.8 | 0% | Provide offline circ transactions file | 0 days | 2017-06-12 16:00 | 2017-06-12 16:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.9 | 0% | Load offline circulation transactions file into Alma | 1 hour | 2017-06-12 16:00 | 2017-06-12 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.10 | 0% | Customer test offline transactions in Alma | 1 hour | 2017-06-12 17:00 | 2017-06-12 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.11 | 0% | Finalize all batch jobs scheduling | 0 days | 2017-06-12 17:00 | 2017-06-12 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.12 | 0% | Milestone: Customer Accept Alma environment | 0 days | 2017-06-12 18:00 | 2017-06-12 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1 | 0% | Primo-Alma integration
| 5.1.1 | 0% | Follow internal STP cloud request steps for Primo | 0 days | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp. | Internal -Documentation Center / General / Company Procedures / Professional Services
| 5.1.2 | 0% | Cloud checks/confirms that STP steps were implemented | 5 days | 2017-05-15 | 2017-05-22 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.3 | 0% | Re-Add Primo S/FTP address to Alma's S/FTP include list and run full Primo publish from Alma | 1/2 day | 2017-06-05 | 2017-06-05 | 3.1.3 | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.4 | 0% | Extract availability file from Alma for Primo Central | 1/2 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.5 | 0% | Load Alma data into Primo & Indexing | 1 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.6 | 0% | Load data from other Customer data sources, if necessary. | 1 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.7 | 0% | Verify Primo with full clean data re-published. | 1 day | 2017-06-11 08:00 | 2017-06-11 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1.8 | 0% | Activate ongoing publishing | 0 days | 2017-06-11 | 2017-06-11 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.9 | 0% | Milestone: Customer Accept Primo-Alma environment | 0 days | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1 | 0% | Go-Live Milestones
| 6.1.1 | 0% | Ensure relevant jobs are enabled/disabled in preparation for go-live process | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 6.1.2 | 0% | Go-Live Process Run/Enabled: 1. Removes 'SCRUBBED_' from all patron and vendor emails. 2. Remove all email and ftp include list entries 3. Enable preferred term correction capability (disable_preferred_term_correction_job=false) 4. Unhide configuration (hide_configuration=false) presuming certification has been completed. 5. Enable scheduled jobs (enable_scheduled_jobs=true) | 1 hour | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | ExL Imp. Updates case with Unscrub request
| 6.1.3 | 0% | Go-Live with Alma | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.4 | 0% | Go-Live with Primo-Alma | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.5 | 0% | All OpenURL compliant data sources point to Primo service page | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.6 | 0% | Complete any relevant data publish to external parties, if relevant (OCLC, Libraries Australia, COPAC, SunCat, HathiTrust, Google Scholar, among others) | .5 day | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.7 | 0% | Complete any load of local Authority records, if relevant. | .5 day | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.8 | 0% | Switch Customer Alma status to 'Live PS' in CRM | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
Formulas:
Internal Use: HQ ST = Table13[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)
Internal Use: HQ FT = Table13[[#This Row],[Finish Date/ Time (Local Cust Time)]]+(O1/24)
Note on E10: Fixed duration
Note on E17: Fixed duration
Note on E18: Fixed duration
Note on E19: Fixed duration
Note on E23: Fixed duration
Note on E24: Fixed duration

## Group 1 Voyager
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Aleph or Voyager Alma Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 0% | Install AutoExtract package/s (Aleph, Voyager and Verde) and Deploys ILS AutoExtract package with the filled-in test load migration form in order to generate an upgraded baseline migration form for cutover Ensure Aleph/Voyager/SFX/Verde servers have pre-requisite disk space. Note: For ExL hosted Aleph, Voyager or Verde customers, ExL will perform this step and provide the generated migration forms. | 2 hours | n/a | n/a | 2.5 weeks prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer (or ExL Migration if product is ExL hosted)
| 1.1.2 | 0% | Provide updated/filled-in migration inputs to ExL project team – ExL project team will update CRM with: 1. Final Migration form (green valid cover page) 2. Draft eResources P2E (final P2E provided/used in step 2.1.7) | 1 day | 2017-05-01 | 2017-05-01 | 10-14 days prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer
| 1.1.3 | 0% | Customer ensure all libraries, locations and vendors in their ILS (and ERM system, if relevant) are reflected in Alma with the same codes in prep for cutover. | 1 day | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1 | 0% | Technical Freeze and Extract/Transform
| 2.1.1 | 0% | ILS backups done | 2 hours | 2017-05-13 19:00 | 2017-05-13 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 02:00 | 2017-05-14 04:00
| 2.1.2 | 0% | Link Resolver (and ERM system, if relevant) backups done | 2 hours | 2017-05-13 19:00 | 2017-05-13 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 02:00 | 2017-05-14 04:00
| 2.1.3 | 0% | Disable all jobs in ILS, Link Resolver (and ERM system, if relevant) | 30 minutes | 2017-05-13 21:00 | 2017-05-13 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 04:00 | 2017-05-14 04:30
MigOps | 2.1.4 | 0% | Freeze config changes on Alma PROD Configuration on Alma should not be done again until data has been reviewed and accepted in step 3.1.8 | 0 days | 2017-05-13 21:30 | 2017-05-13 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer/ExL Imp. |  | 2017-05-14 04:30 | 2017-05-14 04:30
| 2.1.5 | 0% | Export Customer institution from PROD to IMPL | 1 day | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 2.1.6 | 0% | Send confirmation to EXL that tech services freeze (Tech services= everything other than loans, requests and patrons/fines which will continue to be up and running until the fulfillment cutover below) has begun in ILS system and backups and job tasks were completed. | 0 days | 2017-05-13 23:30 | 2017-05-13 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-14 06:30 | 2017-05-14 06:30
| 2.1.7 | 0% | Perform ILS full extract/transform with final valid migration form and P2E input and upload extracted data to S/FTP | 10 hours | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.8 | 0% | Perform Link Resolver full extract/transform and upload to S/FTP | 5 hours | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration for SFX, Customer for Non-EXL LR
| 2.1.9 | 0% | Perform ERM full extract/transform and upload to S/FTP, if necessary | 5 hours | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.10 | 0% | ILS data extract transfer to cloud | 1 day | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.11 | 0% | Link Resolver data extract transfer to cloud | 1 day | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.12 | 0% | ERM data extract transfer to cloud, if necessary | 1 day | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.13 | 0% | Re-enable circ jobs in source ILS ONLY after receiving notification of extract completion | 1 day | 2017-05-13 | 2017-05-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.14 | 0% | Contact all electronic data suppliers with a request to use Primo service page as a link resolver instead of SFX. Must be effective from Primo go-live date | 0 days | 2017-05-13 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1 | 0% | Data load and processing activities
MigOps | 3.1.1 | 0% | Full data load to IMPL | 4 days baseline (Add .5 day per M records) | 2017-05-14 | 2017-06-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | Data released on IMPL for ExL Imp. quick checks of migrated data | 4 hours | 2017-06-01 10:00 | 2017-06-01 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration / ExL Imp. |  | 2017-06-01 17:00 | 2017-06-01 21:00
MigOps | 3.1.3 | 0% | Copy clean data back to PROD | 10 hours | 2017-06-05 14:00 | 2017-06-05 23:59 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-05 21:00 | 2017-06-06 06:59
| 3.1.7 | 0% | Customer data testing of clean data on Prod | 2 days | 2017-06-05 09:00 | 2017-06-07 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1.8 | 0% | Milestone: Customer data acceptance | 0 days | 2017-06-07 17:00 | 2017-06-08 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Fulfillment cutover activities
| 4.1.1 | 0% | Final ILS backup | 2 hours | 2017-06-11 20:00 | 2017-06-11 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-12 03:00 | 2017-06-12 05:00
| 4.1.2 | 0% | Disable all jobs in ILS | 30 minutes | 2017-06-11 22:00 | 2017-06-11 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-12 05:00 | 2017-06-12 05:30
| 4.1.3 | 0% | Send confirmation to EXL that circulation freeze has begun in ILS system and backups and jobs disabling were completed. | 0 days | 2017-06-11 22:30 | 2017-06-11 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-12 05:30 | 2017-06-12 05:30
| 4.1.4 | 0% | Set Primo (and ILS OPAC, if relevant) to read-only | 0 days | 2017-06-11 22:30 | 2017-06-11 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 4.1.5 | 0% | Extract patrons, loans and requests after backup complete | 1/2 day | 2017-06-11 22:30 | 2017-06-11 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-12 05:30 | 2017-06-12 05:30
| 4.1.6 | 0% | Load patrons/fines, loans and requests to Alma | 1/2 day | 2017-06-11 22:30 | 2017-06-11 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-12 05:30 | 2017-06-12 05:30
| 4.1.7 | 0% | Use Alma offline circ | 2 days | 2017-06-11 20:00 | 2017-06-13 08:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer | Need Customer to install Alma offline circ client on fulfillment machines beforehand and test
| 4.1.8 | 0% | Customer data testing of clean patron, loan and request data on Prod | 4 hours | 2017-06-12 10:00 | 2017-06-12 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.9 | 0% | Provide offline circ transactions file | 0 days | 2017-06-12 16:00 | 2017-06-12 16:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.10 | 0% | Load offline circulation transactions file into Alma | 1 hour | 2017-06-12 16:00 | 2017-06-12 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.11 | 0% | Customer test offline transactions in Alma | 1 hour | 2017-06-12 17:00 | 2017-06-12 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.12 | 0% | Finalize all batch jobs scheduling | 0 days | 2017-06-12 17:00 | 2017-06-12 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.13 | 0% | Milestone: Customer Accept Alma environment | 0 days | 2017-06-12 18:00 | 2017-06-12 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1 | 0% | Primo-Alma integration
| 5.1.1 | 0% | Follow internal STP cloud request steps for Primo | 0 days | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp. | Internal -Documentation Center / General / Company Procedures / Professional Services
| 5.1.2 | 0% | Cloud checks/confirms that STP steps were implemented | 5 days | 2017-05-15 | 2017-05-22 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.3 | 0% | Re-Add Primo S/FTP address to Alma's S/FTP include list and run full Primo publish from Alma | 1/2 day | 2017-06-05 | 2017-06-05 | 3.1.3 | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.4 | 0% | Extract availability file from Alma for Primo Central | 1/2 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.5 | 0% | Load Alma data into Primo & Indexing | 1 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.6 | 0% | Load data from other Customer data sources, if necessary. | 1 day | 2017-06-05 | 2017-06-05 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.7 | 0% | Verify Primo with full clean data re-published. | 1 day | 2017-06-11 08:00 | 2017-06-11 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1.8 | 0% | Activate ongoing publishing | 0 days | 2017-06-11 | 2017-06-11 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.9 | 0% | Milestone: Customer Accept Primo-Alma environment | 0 days | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1 | 0% | Go-Live Milestones
| 6.1.1 | 0% | Ensure relevant jobs are enabled/disabled in preparation for go-live process | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 6.1.2 | 0% | Go-Live Process Run/Enabled: 1. Removes 'SCRUBBED_' from all patron and vendor emails. 2. Remove all email and ftp include list entries 3. Enable preferred term correction capability (disable_preferred_term_correction_job=false) 4. Unhide configuration (hide_configuration=false) presuming certification has been completed. 5. Enable scheduled jobs (enable_scheduled_jobs=true) | 1 hour | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | ExL Imp. Updates case with Unscrub request
| 6.1.3 | 0% | Go-Live with Alma | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.4 | 0% | Go-Live with Primo-Alma | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.5 | 0% | All OpenURL compliant data sources point to Primo service page | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.6 | 0% | Complete any relevant data publish to external parties, if relevant (OCLC, Libraries Australia, COPAC, SunCat, HathiTrust, Google Scholar, among others) | .5 day | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.7 | 0% | Complete any load of local Authority records, if relevant. | .5 day | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.8 | 0% | Switch Customer Alma status to 'Live PS' in CRM | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
Formulas:
Internal Use: HQ ST = Table1[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)
Internal Use: HQ FT = Table1[[#This Row],[Finish Date/ Time (Local Cust Time)]]+(O1/24)
Note on E12: Fixed duration
Note on E14: Fixed duration
Note on E15: Fixed duration
Note on E16: Fixed duration
Note on E17: Fixed duration
Note on E18: Fixed duration
Note on E19: Fixed duration
Note on E24: Fixed duration
Note on E25: Fixed duration
Note on E33: Fixed duration
Note on E34: Fixed duration

## Group 1 Alma-to-Alma
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Joining Network Zone - Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 100% | Extract 773 information from customer records |  | 2017-06-06 | 2017-06-06 |  | Customer Contact Name | ExL Imp. Contact Name | Customer | ?? Is this needed for CSU?
| 2.1 | 0% | Technical Freeze
|  | 100% | No further lending ILL requests are processed on customer |  | 2017-06-06 17:00 | 2017-06-06 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
|  | 100% | Last metadata import in 'old' environment |  | 2017-06-06 | 2017-06-06 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.3 | 100% | Set Primo to read-only | 30 minutes | 2017-06-06 17:00 | 2017-06-06 17:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.4 | 100% | Technical Freeze on customer live IZ | 0 hours | 2017-06-06 20:00 | 2017-06-06 20:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.1 | 100% | De-active scheduled jobs in customer parameters enable_scheduled_jobs = false | 30 minutes | 2017-06-06 20:00 | 2017-06-06 20:15 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 2.1.2 | 100% | Set FTP and Email include lists to exlibrisgroup.com to ensure no Alma customer email or ftp communication is done during technical freeze. | 30 minutes | 2017-06-06 20:15 | 2017-06-06 20:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 3.1 | 0% | Instance move and processing activities
MigOps | 3.1.1 | 100% | Copy customer live instance to CSU NZ environment and link to CSU NZ | 2 days | 2017-06-07 | 2017-06-08 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | De-activate all users except select staff on “old” customer env | 1 hour | 2017-06-08 | 2017-06-08 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 3.1.3 | 100% | Re-direct customer Alma URL to customer@CSU NZ | 30 minutes | 2017-06-08 | 2017-06-08 |  | Customer Contact Name | ExL Imp. Contact Name | Cloud Services
| 3.1.4 | 100% | Run "Build MMS Relation" job on customer@CSU NZ | ? | 2017-06-08 | 2017-06-08 |  | Customer Contact Name | ExL Imp. Contact Name | Exl Migration | Can continue in the background, if not finished by end date
| 3.1.5 | 100% | Adjust logo/color of the ‘old’ customer env to prevent any further usage | 20 minutes | 2017-06-08 09:00 | 2017-06-08 09:20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 3.1.6 | 100% | Initial data tests on customer@CSU NZ | 40 minutes | 2017-06-08 09:20 | 2017-06-08 10:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 3.1.7 | 100% | Milestone: Hand over to customer | 0 hours | 2017-06-08 10:00 | 2017-06-08 10:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 3.2.2 | 100% | Re-direct Primo URLs in Alma config, Google scholar, and APIs to customer@CSU NZ | 30 minutes | 2017-06-08 10:00 | 2017-06-08 10:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 3.2.3 | 100% | Creation of data set "multi matches" | 1 hour | 2017-06-08 10:00 | 2017-06-08 11:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.2.4 | 100% | Deleting multi-matching IDs on customer@CSU NZ | 1 hour | 2017-06-08 11:00 | 2017-06-08 12:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.2.5 | 100% | Run Job "Link records to the Network Zone" for data set "multi matches" | 30 minutes | 2017-06-08 12:00 | 2017-06-08 12:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 42895 | 2017-06-08 19:00
| 3.2.6 | 50% | Customer initial data tests | 1 hour | 2017-06-09 10:00 | 2017-06-09 11:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 3.2.7 | 0% | Connect customer Primo to customer@CSU NZ and set back to read/write | 1 hour | 2017-06-09 11:00 | 2017-06-09 12:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.2.8 | 0% | Testing: Alma and Primo interoperability / user interface | 2 hours | 2017-06-09 12:00 | 2017-06-09 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.2.9 | 0% | Milestone: Customer environment acceptance = customer@CSU NZ live (internal + Primo) | 0 days | 2017-06-09 16:00 | 2017-06-09 16:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Integration Work
| 4.1.1 | 0% | Activate publishing from customer@CSU NZ to Primo production and monitor the pipe | 1 hours | 2017-06-11 16:00 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.2 | 100% | Switch self check (circulation machines and book return stations) to customer@CSU NZ and test | 1 day | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.3 | 0% | Test other 3rd party tools/integrations | 0 days | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.4 | 0% | Milestone: Alma fully live on CSU NZ - all integrations tested and up and running | 0 days | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.5 | 0% | Block all traffic/access to “old” customer environment | 1 day | 2017-06-13 | 2017-06-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL (David)
| 5.1 | 0% | Post Go-Live Activity
| 5.1.1 | 0% | Refresh customer premium SB with IZ + CSU NZ | 1 day | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Cloud Services | 2 weeks after go live
| 5.1.2 | 0% | De-provision “old” customer environment |  | 2017-09-13 | 2017-09-13 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | 3 months after go live
Formulas:
Internal Use: HQ FT = Table17[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)

## Group 2 Innovative
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Non-EXL ILS Alma Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 0% | Provide updated migration inputs to ExL project team – ExL project team will update CRM with: 1. Final Migration form (green valid cover page) 2. Final Mapped fields (green valid cover page) 3. Draft eResources P2E (final P2E provided/used in step 2.1.9) 4. Draft Delivered files Excel list indicating the files provided and their attributes | 1 day | 2017-05-08 | 2017-05-08 | 2 weeks prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer
| 1.1.2 | 0% | Customer ensure all libraries, locations and vendors in their ILS (and ERM system, if relevant) are reflected in Alma with the same codes in prep for cutover. | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1 | 0% | Technical Freeze and Extract/Transform
| 2.1.1 | 0% | ILS backups done | 2 hours | 2017-05-20 19:00 | 2017-05-20 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 02:00 | 2017-05-21 04:00
| 2.1.2 | 0% | Link Resolver (and ERM system, if relevant) backups done | 2 hours | 2017-05-20 19:00 | 2017-05-20 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 02:00 | 2017-05-21 04:00
MigOps | 2.1.3 | 0% | Freeze config changes on Alma PROD Configuration on Alma should not be done again until data has been reviewed and accepted in step 3.1.8 | 0 days | 2017-05-20 21:30 | 2017-05-20 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer/ExL Imp. |  | 2017-05-21 04:30 | 2017-05-21 04:30
| 2.1.4 | 0% | Export Customer institution from PROD to IMPL | 1 day | 2017-05-21 | 2017-05-21 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.5 | 0% | Freeze Technical services in ILS, LR (and ERM, if necessary). (Tech services= everything other than loans, requests and patrons/fines which will continue to be up and running until the fulfillment cutover below). Circulation activity continues (Patrons/fines, loans, requests). | 0 days | 2017-05-20 23:30 | 2017-05-20 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 06:30 | 2017-05-21 06:30
| 2.1.6 | 0% | Perform ILS full extract of all data in scope, as contracted with ExL and delivered at test load. | 10 hours | 2017-05-20 23:30 | 2017-05-20 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.7 | 0% | Perform Link Resolver full extract | 5 hours | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.8 | 0% | Perform ERM full extract, if necessary | 5 hours | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.9 | 0% | Upload ILS data to ExL S/FTP along with: 1. Final eResources P2E file 2. Final Delivered files Excel list indicating the files provided and their attributes | 5 hours | 2017-05-20 23:30 | 2017-05-20 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 06:30 | 2017-05-21 06:30
MigOps | 2.1.10 | 0% | Send confirmation to EXL that data is ready to download. | 0 days | 2017-05-20 23:30 | 2017-05-20 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 06:30 | 2017-05-21 06:30
| 2.1.11 | 0% | ILS data extract transfer to cloud | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.12 | 0% | Link Resolver data extract transfer to cloud | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.13 | 0% | ERM data extract transfer to cloud, if necessary | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.14 | 0% | Contact all electronic data suppliers with a request to use Primo service page as a link resolver instead of SFX. Must be effective from Primo go-live date | 0 days | 2017-05-20 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1 | 0% | Data load and processing activities
MigOps | 3.1.1 | 0% | Full data transform and load to IMPL | 5 days baseline (Add .5 day for each 1M records) | 2017-05-21 | 2017-06-08 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | Data released on IMPL for ExL Imp. quick checks of migrated data | 4 hours | 2017-06-08 | 2017-06-11 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration / ExL Imp. |  | 2017-06-08 07:00 | 2017-06-11 07:00
MigOps | 3.1.3 | 0% | Copy clean data back to PROD | 10 hours | 2017-06-12 | 2017-06-12 10:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-12 07:00 | 2017-06-12 17:00
| 3.1.7 | 0% | Customer data testing of clean data on Prod | 2 days | 2017-06-12 | 2017-06-14 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1.8 | 0% | Milestone: Customer data acceptance | 0 days | 2017-06-14 17:00 | 2017-06-14 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Fulfillment cutover activities
| 4.1.1 | 0% | Final ILS backup | 2 hours | 2017-06-18 20:00 | 2017-06-18 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-19 03:00 | 2017-06-19 05:00
| 4.1.2 | 0% | Perform final ILS extract of patrons, loans and requests. | 2 hours | 2017-06-18 20:00 | 2017-06-18 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-19 03:00 | 2017-06-19 05:00
| 4.1.3 | 0% | Send confirmation to EXL that fufillment data (patrons, loans and requests) are ready for download | 0 days | 2017-06-18 22:00 | 2017-06-18 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-19 05:00 | 2017-06-19 05:00
| 4.1.4 | 0% | Set Primo (and ILS OPAC, if relevant) to read-only | 0 days | 2017-06-18 22:00 | 2017-06-18 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 4.1.5 | 0% | Transform and load patrons, loans and requests to Alma | 1 day | 2017-06-18 22:30 | 2017-06-18 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-19 05:30 | 2017-06-19 05:30
| 4.1.7 | 0% | Use Alma offline circ | 2 days | 2017-06-18 20:00 | 2017-06-20 08:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer | Need Customer to install Alma offline circ client on fulfillment machines beforehand and test
| 4.1.6 | 0% | Customer data testing of clean patron, loan and request data on Prod | 4 hours | 2017-06-18 10:00 | 2017-06-18 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.8 | 0% | Provide offline circ transactions file | 0 days | 2017-06-19 16:00 | 2017-06-19 16:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.9 | 0% | Load offline circulation transactions file into Alma | 1 hour | 2017-06-19 16:00 | 2017-06-19 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.10 | 0% | Customer test offline transactions in Alma | 1 hour | 2017-06-19 17:00 | 2017-06-19 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.11 | 0% | Finalize all batch jobs scheduling | 0 days | 2017-06-19 17:00 | 2017-06-19 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.12 | 0% | Milestone: Customer Accept Alma environment | 0 days | 2017-06-19 18:00 | 2017-06-19 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1 | 0% | Primo-Alma integration
| 5.1.1 | 0% | Follow internal STP cloud request steps for Primo | 0 days | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp. | Internal -Documentation Center / General / Company Procedures / Professional Services
| 5.1.2 | 0% | Cloud checks/confirms that STP steps were implemented | 5 days | 2017-05-15 | 2017-05-22 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.3 | 0% | Re-Add Primo S/FTP address to Alma's S/FTP include list and run full Primo publish from Alma | 1/2 day | 2017-06-12 | 2017-06-12 | 3.1.3 | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.4 | 0% | Extract availability file from Alma for Primo Central | 1/2 day | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.5 | 0% | Load Alma data into Primo & Indexing | 1 day | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.6 | 0% | Load data from other Customer data sources, if necessary. | 1 day | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.7 | 0% | Verify Primo with full clean data re-published. | 1 day | 2017-06-18 08:00 | 2017-06-18 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1.8 | 0% | Activate ongoing publishing | 0 days | 2017-06-18 | 2017-06-18 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.9 | 0% | Milestone: Customer Accept Primo-Alma environment | 0 days | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1 | 0% | Go-Live Milestones
| 6.1.1 | 0% | Ensure relevant jobs are enabled/disabled in preparation for go-live process | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 6.1.2 | 0% | Go-Live Process Run/Enabled: 1. Removes 'SCRUBBED_' from all patron and vendor emails. 2. Remove all email and ftp include list entries 3. Enable preferred term correction capability (disable_preferred_term_correction_job=false) 4. Unhide configuration (hide_configuration=false) presuming certification has been completed. 5. Enable scheduled jobs (enable_scheduled_jobs=true) | 1 hour | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | ExL Imp. Updates case with Unscrub request
| 6.1.3 | 0% | Go-Live with Alma | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.4 | 0% | Go-Live with Primo-Alma | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.5 | 0% | All OpenURL compliant data sources point to Primo service page | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.6 | 0% | Complete any relevant data publish to external parties, if relevant (OCLC, Libraries Australia, COPAC, SunCat, HathiTrust, Google Scholar, among others) | .5 day | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.7 | 0% | Complete any load of local Authority records, if relevant. | .5 day | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.8 | 0% | Switch Customer Alma status to 'Live PS' in CRM | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
Formulas:
Internal Use: HQ ST = Table132[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)
Internal Use: HQ FT = Table132[[#This Row],[Finish Date/ Time (Local Cust Time)]]+(O1/24)
Note on E10: Fixed duration
Note on E17: Fixed duration
Note on E18: Fixed duration
Note on E19: Fixed duration
Note on E23: Fixed duration
Note on E24: Fixed duration

## Group 2 Voyager
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Aleph or Voyager Alma Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 0% | Install AutoExtract package/s (Aleph, Voyager and Verde) and Deploys ILS AutoExtract package with the filled-in test load migration form in order to generate an upgraded baseline migration form for cutover Ensure Aleph/Voyager/SFX/Verde servers have pre-requisite disk space. Note: For ExL hosted Aleph, Voyager or Verde customers, ExL will perform this step and provide the generated migration forms. | 2 hours | n/a | n/a | 2.5 weeks prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer (or ExL Migration if product is ExL hosted)
| 1.1.2 | 0% | Provide updated/filled-in migration inputs to ExL project team – ExL project team will update CRM with: 1. Final Migration form (green valid cover page) 2. Draft eResources P2E (final P2E provided/used in step 2.1.7) | 1 day | 2017-05-08 | 2017-05-08 | 10-14 days prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer
| 1.1.3 | 0% | Customer ensure all libraries, locations and vendors in their ILS (and ERM system, if relevant) are reflected in Alma with the same codes in prep for cutover. | 1 day | 2017-05-08 | 2017-05-08 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1 | 0% | Technical Freeze and Extract/Transform
| 2.1.1 | 0% | ILS backups done | 2 hours | 2017-05-20 19:00 | 2017-05-20 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 02:00 | 2017-05-21 04:00
| 2.1.2 | 0% | Link Resolver (and ERM system, if relevant) backups done | 2 hours | 2017-05-20 19:00 | 2017-05-20 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 02:00 | 2017-05-21 04:00
| 2.1.3 | 0% | Disable all jobs in ILS, Link Resolver (and ERM system, if relevant) | 30 minutes | 2017-05-20 21:00 | 2017-05-20 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 04:00 | 2017-05-21 04:30
MigOps | 2.1.4 | 0% | Freeze config changes on Alma PROD Configuration on Alma should not be done again until data has been reviewed and accepted in step 3.1.8 | 0 days | 2017-05-20 21:30 | 2017-05-20 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer/ExL Imp. |  | 2017-05-21 04:30 | 2017-05-21 04:30
| 2.1.5 | 0% | Export Customer institution from PROD to IMPL | 1 day | 2017-05-21 | 2017-05-21 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 2.1.6 | 0% | Send confirmation to EXL that tech services freeze (Tech services= everything other than loans, requests and patrons/fines which will continue to be up and running until the fulfillment cutover below) has begun in ILS system and backups and job tasks were completed. | 0 days | 2017-05-20 23:30 | 2017-05-20 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-21 06:30 | 2017-05-21 06:30
| 2.1.7 | 0% | Perform ILS full extract/transform with final valid migration form and P2E input and upload extracted data to S/FTP | 10 hours | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.8 | 0% | Perform Link Resolver full extract/transform and upload to S/FTP | 5 hours | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration for SFX, Customer for Non-EXL LR
| 2.1.9 | 0% | Perform ERM full extract/transform and upload to S/FTP, if necessary | 5 hours | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.10 | 0% | ILS data extract transfer to cloud | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.11 | 0% | Link Resolver data extract transfer to cloud | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.12 | 0% | ERM data extract transfer to cloud, if necessary | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.13 | 0% | Re-enable circ jobs in source ILS ONLY after receiving notification of extract completion | 1 day | 2017-05-20 | 2017-05-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.14 | 0% | Contact all electronic data suppliers with a request to use Primo service page as a link resolver instead of SFX. Must be effective from Primo go-live date | 0 days | 2017-05-20 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1 | 0% | Data load and processing activities
MigOps | 3.1.1 | 0% | Full data load to IMPL | 4 days baseline (Add .5 day per M records) | 2017-05-21 | 2017-06-08 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | Data released on IMPL for ExL Imp. quick checks of migrated data | 4 hours | 2017-06-08 10:00 | 2017-06-08 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration / ExL Imp. |  | 2017-06-08 17:00 | 2017-06-08 21:00
MigOps | 3.1.3 | 0% | Copy clean data back to PROD | 10 hours | 2017-06-12 14:00 | 2017-06-12 23:59 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-12 21:00 | 2017-06-13 06:59
| 3.1.7 | 0% | Customer data testing of clean data on Prod | 2 days | 2017-06-12 09:00 | 2017-06-14 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1.8 | 0% | Milestone: Customer data acceptance | 0 days | 2017-06-14 17:00 | 2017-06-15 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Fulfillment cutover activities
| 4.1.1 | 0% | Final ILS backup | 2 hours | 2017-06-18 20:00 | 2017-06-18 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-19 03:00 | 2017-06-19 05:00
| 4.1.2 | 0% | Disable all jobs in ILS | 30 minutes | 2017-06-18 22:00 | 2017-06-18 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-19 05:00 | 2017-06-19 05:30
| 4.1.3 | 0% | Send confirmation to EXL that circulation freeze has begun in ILS system and backups and jobs disabling were completed. | 0 days | 2017-06-18 22:30 | 2017-06-18 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-19 05:30 | 2017-06-19 05:30
| 4.1.4 | 0% | Set Primo (and ILS OPAC, if relevant) to read-only | 0 days | 2017-06-18 22:30 | 2017-06-18 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 4.1.5 | 0% | Extract patrons, loans and requests after backup complete | 1/2 day | 2017-06-18 22:30 | 2017-06-18 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-19 05:30 | 2017-06-19 05:30
| 4.1.6 | 0% | Load patrons/fines, loans and requests to Alma | 1/2 day | 2017-06-18 22:30 | 2017-06-18 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-19 05:30 | 2017-06-19 05:30
| 4.1.7 | 0% | Use Alma offline circ | 2 days | 2017-06-18 20:00 | 2017-06-20 08:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer | Need Customer to install Alma offline circ client on fulfillment machines beforehand and test
| 4.1.8 | 0% | Customer data testing of clean patron, loan and request data on Prod | 4 hours | 2017-06-19 10:00 | 2017-06-19 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.9 | 0% | Provide offline circ transactions file | 0 days | 2017-06-19 16:00 | 2017-06-19 16:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.10 | 0% | Load offline circulation transactions file into Alma | 1 hour | 2017-06-19 16:00 | 2017-06-19 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.11 | 0% | Customer test offline transactions in Alma | 1 hour | 2017-06-19 17:00 | 2017-06-19 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.12 | 0% | Finalize all batch jobs scheduling | 0 days | 2017-06-19 17:00 | 2017-06-19 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.13 | 0% | Milestone: Customer Accept Alma environment | 0 days | 2017-06-19 18:00 | 2017-06-19 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1 | 0% | Primo-Alma integration
| 5.1.1 | 0% | Follow internal STP cloud request steps for Primo | 0 days | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp. | Internal -Documentation Center / General / Company Procedures / Professional Services
| 5.1.2 | 0% | Cloud checks/confirms that STP steps were implemented | 5 days | 2017-05-15 | 2017-05-22 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.3 | 0% | Re-Add Primo S/FTP address to Alma's S/FTP include list and run full Primo publish from Alma | 1/2 day | 2017-06-12 | 2017-06-12 | 3.1.3 | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.4 | 0% | Extract availability file from Alma for Primo Central | 1/2 day | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.5 | 0% | Load Alma data into Primo & Indexing | 1 day | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.6 | 0% | Load data from other Customer data sources, if necessary. | 1 day | 2017-06-12 | 2017-06-12 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.7 | 0% | Verify Primo with full clean data re-published. | 1 day | 2017-06-18 08:00 | 2017-06-18 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1.8 | 0% | Activate ongoing publishing | 0 days | 2017-06-18 | 2017-06-18 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.9 | 0% | Milestone: Customer Accept Primo-Alma environment | 0 days | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1 | 0% | Go-Live Milestones
| 6.1.1 | 0% | Ensure relevant jobs are enabled/disabled in preparation for go-live process | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 6.1.2 | 0% | Go-Live Process Run/Enabled: 1. Removes 'SCRUBBED_' from all patron and vendor emails. 2. Remove all email and ftp include list entries 3. Enable preferred term correction capability (disable_preferred_term_correction_job=false) 4. Unhide configuration (hide_configuration=false) presuming certification has been completed. 5. Enable scheduled jobs (enable_scheduled_jobs=true) | 1 hour | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | ExL Imp. Updates case with Unscrub request
| 6.1.3 | 0% | Go-Live with Alma | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.4 | 0% | Go-Live with Primo-Alma | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.5 | 0% | All OpenURL compliant data sources point to Primo service page | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.6 | 0% | Complete any relevant data publish to external parties, if relevant (OCLC, Libraries Australia, COPAC, SunCat, HathiTrust, Google Scholar, among others) | .5 day | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.7 | 0% | Complete any load of local Authority records, if relevant. | .5 day | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.8 | 0% | Switch Customer Alma status to 'Live PS' in CRM | 0 days | 2017-06-20 | 2017-06-20 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
Formulas:
Internal Use: HQ ST = Table16[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)
Internal Use: HQ FT = Table16[[#This Row],[Finish Date/ Time (Local Cust Time)]]+(O1/24)
Note on E12: Fixed duration
Note on E14: Fixed duration
Note on E15: Fixed duration
Note on E16: Fixed duration
Note on E17: Fixed duration
Note on E18: Fixed duration
Note on E19: Fixed duration
Note on E24: Fixed duration
Note on E25: Fixed duration
Note on E33: Fixed duration
Note on E34: Fixed duration

## Group 3 Innovative
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Non-EXL ILS Alma Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 0% | Provide updated migration inputs to ExL project team – ExL project team will update CRM with: 1. Final Migration form (green valid cover page) 2. Final Mapped fields (green valid cover page) 3. Draft eResources P2E (final P2E provided/used in step 2.1.9) 4. Draft Delivered files Excel list indicating the files provided and their attributes | 1 day | 2017-05-15 | 2017-05-15 | 2 weeks prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer
| 1.1.2 | 0% | Customer ensure all libraries, locations and vendors in their ILS (and ERM system, if relevant) are reflected in Alma with the same codes in prep for cutover. | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1 | 0% | Technical Freeze and Extract/Transform
| 2.1.1 | 0% | ILS backups done | 2 hours | 2017-05-27 19:00 | 2017-05-27 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 02:00 | 2017-05-28 04:00
| 2.1.2 | 0% | Link Resolver (and ERM system, if relevant) backups done | 2 hours | 2017-05-27 19:00 | 2017-05-27 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 02:00 | 2017-05-28 04:00
MigOps | 2.1.3 | 0% | Freeze config changes on Alma PROD Configuration on Alma should not be done again until data has been reviewed and accepted in step 3.1.8 | 0 days | 2017-05-27 21:30 | 2017-05-27 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer/ExL Imp. |  | 2017-05-28 04:30 | 2017-05-28 04:30
| 2.1.4 | 0% | Export Customer institution from PROD to IMPL | 1 day | 2017-05-28 | 2017-05-28 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.5 | 0% | Freeze Technical services in ILS, LR (and ERM, if necessary). (Tech services= everything other than loans, requests and patrons/fines which will continue to be up and running until the fulfillment cutover below). Circulation activity continues (Patrons/fines, loans, requests). | 0 days | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 06:30 | 2017-05-28 06:30
| 2.1.6 | 0% | Perform ILS full extract of all data in scope, as contracted with ExL and delivered at test load. | 10 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.7 | 0% | Perform Link Resolver full extract | 5 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.8 | 0% | Perform ERM full extract, if necessary | 5 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.9 | 0% | Upload ILS data to ExL S/FTP along with: 1. Final eResources P2E file 2. Final Delivered files Excel list indicating the files provided and their attributes | 5 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 06:30 | 2017-05-28 06:30
MigOps | 2.1.10 | 0% | Send confirmation to EXL that data is ready to download. | 0 days | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 06:30 | 2017-05-28 06:30
| 2.1.11 | 0% | ILS data extract transfer to cloud | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.12 | 0% | Link Resolver data extract transfer to cloud | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.13 | 0% | ERM data extract transfer to cloud, if necessary | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.14 | 0% | Contact all electronic data suppliers with a request to use Primo service page as a link resolver instead of SFX. Must be effective from Primo go-live date | 0 days | 2017-05-27 | 2017-06-26 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1 | 0% | Data load and processing activities
MigOps | 3.1.1 | 0% | Full data transform and load to IMPL | 5 days baseline (Add .5 day for each 1M records) | 2017-05-28 | 2017-06-15 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | Data released on IMPL for ExL Imp. quick checks of migrated data | 4 hours | 2017-06-15 | 2017-06-18 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration / ExL Imp. |  | 2017-06-15 07:00 | 2017-06-18 07:00
MigOps | 3.1.3 | 0% | Copy clean data back to PROD | 10 hours | 2017-06-19 | 2017-06-19 10:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-19 07:00 | 2017-06-19 17:00
| 3.1.7 | 0% | Customer data testing of clean data on Prod | 2 days | 2017-06-19 | 2017-06-21 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1.8 | 0% | Milestone: Customer data acceptance | 0 days | 2017-06-21 17:00 | 2017-06-21 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Fulfillment cutover activities
| 4.1.1 | 0% | Final ILS backup | 2 hours | 2017-06-25 20:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-26 03:00 | 2017-06-26 05:00
| 4.1.2 | 0% | Perform final ILS extract of patrons, loans and requests. | 2 hours | 2017-06-25 20:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-26 03:00 | 2017-06-26 05:00
| 4.1.3 | 0% | Send confirmation to EXL that fufillment data (patrons, loans and requests) are ready for download | 0 days | 2017-06-25 22:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-26 05:00 | 2017-06-26 05:00
| 4.1.4 | 0% | Set Primo (and ILS OPAC, if relevant) to read-only | 0 days | 2017-06-25 22:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 4.1.5 | 0% | Transform and load patrons, loans and requests to Alma | 1 day | 2017-06-25 22:30 | 2017-06-25 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-26 05:30 | 2017-06-26 05:30
| 4.1.7 | 0% | Use Alma offline circ | 2 days | 2017-06-25 20:00 | 2017-06-27 08:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer | Need Customer to install Alma offline circ client on fulfillment machines beforehand and test
| 4.1.6 | 0% | Customer data testing of clean patron, loan and request data on Prod | 4 hours | 2017-06-25 10:00 | 2017-06-25 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.8 | 0% | Provide offline circ transactions file | 0 days | 2017-06-26 16:00 | 2017-06-26 16:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.9 | 0% | Load offline circulation transactions file into Alma | 1 hour | 2017-06-26 16:00 | 2017-06-26 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.10 | 0% | Customer test offline transactions in Alma | 1 hour | 2017-06-26 17:00 | 2017-06-26 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.11 | 0% | Finalize all batch jobs scheduling | 0 days | 2017-06-26 17:00 | 2017-06-26 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.12 | 0% | Milestone: Customer Accept Alma environment | 0 days | 2017-06-26 18:00 | 2017-06-26 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1 | 0% | Primo-Alma integration
| 5.1.1 | 0% | Follow internal STP cloud request steps for Primo | 0 days | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp. | Internal -Documentation Center / General / Company Procedures / Professional Services
| 5.1.2 | 0% | Cloud checks/confirms that STP steps were implemented | 5 days | 2017-05-15 | 2017-05-22 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.3 | 0% | Re-Add Primo S/FTP address to Alma's S/FTP include list and run full Primo publish from Alma | 1/2 day | 2017-06-19 | 2017-06-19 | 3.1.3 | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.4 | 0% | Extract availability file from Alma for Primo Central | 1/2 day | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.5 | 0% | Load Alma data into Primo & Indexing | 1 day | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.6 | 0% | Load data from other Customer data sources, if necessary. | 1 day | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.7 | 0% | Verify Primo with full clean data re-published. | 1 day | 2017-06-25 | 2017-06-25 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1.8 | 0% | Activate ongoing publishing | 0 days | 2017-06-25 | 2017-06-25 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.9 | 0% | Milestone: Customer Accept Primo-Alma environment | 0 days | 2017-06-26 | 2017-06-26 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1 | 0% | Go-Live Milestones
| 6.1.1 | 0% | Ensure relevant jobs are enabled/disabled in preparation for go-live process | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 6.1.2 | 0% | Go-Live Process Run/Enabled: 1. Removes 'SCRUBBED_' from all patron and vendor emails. 2. Remove all email and ftp include list entries 3. Enable preferred term correction capability (disable_preferred_term_correction_job=false) 4. Unhide configuration (hide_configuration=false) presuming certification has been completed. 5. Enable scheduled jobs (enable_scheduled_jobs=true) | 1 hour | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | ExL Imp. Updates case with Unscrub request
| 6.1.3 | 0% | Go-Live with Alma | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.4 | 0% | Go-Live with Primo-Alma | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.5 | 0% | All OpenURL compliant data sources point to Primo service page | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.6 | 0% | Complete any relevant data publish to external parties, if relevant (OCLC, Libraries Australia, COPAC, SunCat, HathiTrust, Google Scholar, among others) | .5 day | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.7 | 0% | Complete any load of local Authority records, if relevant. | .5 day | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.8 | 0% | Switch Customer Alma status to 'Live PS' in CRM | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
Formulas:
Internal Use: HQ ST = Table1324[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)
Internal Use: HQ FT = Table1324[[#This Row],[Finish Date/ Time (Local Cust Time)]]+(O1/24)
Note on E10: Fixed duration
Note on E17: Fixed duration
Note on E18: Fixed duration
Note on E19: Fixed duration
Note on E23: Fixed duration
Note on E24: Fixed duration

## Group 3 Koha
Internal | Step | Percent_Complete | Name | Duration | Start Date/Time (Local Cust Time) | Finish Date/ Time (Local Cust Time) | Pre-Req | Customer Contact | ExL Contact | Responsible | Notes | Internal Use: HQ ST | Internal Use: HQ FT | 7
|  | 0% | Non-EXL ILS Alma Cutover Plan
| 1.1 | 0% | Pre-Cutover activities
| 1.1.1 | 0% | Provide updated migration inputs to ExL project team – ExL project team will update CRM with: 1. Final Migration form (green valid cover page) 2. Final Mapped fields (green valid cover page) 3. Draft eResources P2E (final P2E provided/used in step 2.1.9) 4. Draft Delivered files Excel list indicating the files provided and their attributes | 1 day | 2017-05-15 | 2017-05-15 | 2 weeks prior to technical freeze | Customer Contact Name | ExL Imp. Contact Name | Customer
| 1.1.2 | 0% | Customer ensure all libraries, locations and vendors in their ILS (and ERM system, if relevant) are reflected in Alma with the same codes in prep for cutover. | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1 | 0% | Technical Freeze and Extract/Transform
| 2.1.1 | 0% | ILS backups done | 2 hours | 2017-05-27 19:00 | 2017-05-27 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 02:00 | 2017-05-28 04:00
| 2.1.2 | 0% | Link Resolver (and ERM system, if relevant) backups done | 2 hours | 2017-05-27 19:00 | 2017-05-27 21:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 02:00 | 2017-05-28 04:00
MigOps | 2.1.3 | 0% | Freeze config changes on Alma PROD Configuration on Alma should not be done again until data has been reviewed and accepted in step 3.1.8 | 0 days | 2017-05-27 21:30 | 2017-05-27 21:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer/ExL Imp. |  | 2017-05-28 04:30 | 2017-05-28 04:30
| 2.1.4 | 0% | Export Customer institution from PROD to IMPL | 1 day | 2017-05-28 | 2017-05-28 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.5 | 0% | Freeze Technical services in ILS, LR (and ERM, if necessary). (Tech services= everything other than loans, requests and patrons/fines which will continue to be up and running until the fulfillment cutover below). Circulation activity continues (Patrons/fines, loans, requests). | 0 days | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 06:30 | 2017-05-28 06:30
| 2.1.6 | 0% | Perform ILS full extract of all data in scope, as contracted with ExL and delivered at test load. | 10 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.7 | 0% | Perform Link Resolver full extract | 5 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.8 | 0% | Perform ERM full extract, if necessary | 5 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 2.1.9 | 0% | Upload ILS data to ExL S/FTP along with: 1. Final eResources P2E file 2. Final Delivered files Excel list indicating the files provided and their attributes | 5 hours | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 06:30 | 2017-05-28 06:30
MigOps | 2.1.10 | 0% | Send confirmation to EXL that data is ready to download. | 0 days | 2017-05-27 23:30 | 2017-05-27 23:30 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-05-28 06:30 | 2017-05-28 06:30
| 2.1.11 | 0% | ILS data extract transfer to cloud | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.12 | 0% | Link Resolver data extract transfer to cloud | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.13 | 0% | ERM data extract transfer to cloud, if necessary | 1 day | 2017-05-27 | 2017-05-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
| 2.1.14 | 0% | Contact all electronic data suppliers with a request to use Primo service page as a link resolver instead of SFX. Must be effective from Primo go-live date | 0 days | 2017-05-27 | 2017-06-26 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1 | 0% | Data load and processing activities
MigOps | 3.1.1 | 0% | Full data transform and load to IMPL | 5 days baseline (Add .5 day for each 1M records) | 2017-05-28 | 2017-06-15 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration
MigOps | 3.1.2 | 0% | Data released on IMPL for ExL Imp. quick checks of migrated data | 4 hours | 2017-06-15 | 2017-06-18 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration / ExL Imp. |  | 2017-06-15 07:00 | 2017-06-18 07:00
MigOps | 3.1.3 | 0% | Copy clean data back to PROD | 10 hours | 2017-06-19 | 2017-06-19 10:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-19 07:00 | 2017-06-19 17:00
| 3.1.7 | 0% | Customer data testing of clean data on Prod | 2 days | 2017-06-19 | 2017-06-21 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 3.1.8 | 0% | Milestone: Customer data acceptance | 0 days | 2017-06-21 17:00 | 2017-06-21 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1 | 0% | Fulfillment cutover activities
| 4.1.1 | 0% | Final ILS backup | 2 hours | 2017-06-25 20:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-26 03:00 | 2017-06-26 05:00
| 4.1.2 | 0% | Perform final ILS extract of patrons, loans and requests. | 2 hours | 2017-06-25 20:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-26 03:00 | 2017-06-26 05:00
| 4.1.3 | 0% | Send confirmation to EXL that fufillment data (patrons, loans and requests) are ready for download | 0 days | 2017-06-25 22:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer |  | 2017-06-26 05:00 | 2017-06-26 05:00
| 4.1.4 | 0% | Set Primo (and ILS OPAC, if relevant) to read-only | 0 days | 2017-06-25 22:00 | 2017-06-25 22:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
MigOps | 4.1.5 | 0% | Transform and load patrons, loans and requests to Alma | 1 day | 2017-06-25 22:30 | 2017-06-25 22:30 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration |  | 2017-06-26 05:30 | 2017-06-26 05:30
| 4.1.7 | 0% | Use Alma offline circ | 2 days | 2017-06-25 20:00 | 2017-06-27 08:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer | Need Customer to install Alma offline circ client on fulfillment machines beforehand and test
| 4.1.6 | 0% | Customer data testing of clean patron, loan and request data on Prod | 4 hours | 2017-06-25 10:00 | 2017-06-25 14:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.8 | 0% | Provide offline circ transactions file | 0 days | 2017-06-26 16:00 | 2017-06-26 16:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.9 | 0% | Load offline circulation transactions file into Alma | 1 hour | 2017-06-26 16:00 | 2017-06-26 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.10 | 0% | Customer test offline transactions in Alma | 1 hour | 2017-06-26 17:00 | 2017-06-26 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 4.1.11 | 0% | Finalize all batch jobs scheduling | 0 days | 2017-06-26 17:00 | 2017-06-26 17:00 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 4.1.12 | 0% | Milestone: Customer Accept Alma environment | 0 days | 2017-06-26 18:00 | 2017-06-26 18:00 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1 | 0% | Primo-Alma integration
| 5.1.1 | 0% | Follow internal STP cloud request steps for Primo | 0 days | 2017-05-01 | 2017-05-01 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp. | Internal -Documentation Center / General / Company Procedures / Professional Services
| 5.1.2 | 0% | Cloud checks/confirms that STP steps were implemented | 5 days | 2017-05-15 | 2017-05-22 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.3 | 0% | Re-Add Primo S/FTP address to Alma's S/FTP include list and run full Primo publish from Alma | 1/2 day | 2017-06-19 | 2017-06-19 | 3.1.3 | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.4 | 0% | Extract availability file from Alma for Primo Central | 1/2 day | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.5 | 0% | Load Alma data into Primo & Indexing | 1 day | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.6 | 0% | Load data from other Customer data sources, if necessary. | 1 day | 2017-06-19 | 2017-06-19 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.7 | 0% | Verify Primo with full clean data re-published. | 1 day | 2017-06-25 | 2017-06-25 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 5.1.8 | 0% | Activate ongoing publishing | 0 days | 2017-06-25 | 2017-06-25 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 5.1.9 | 0% | Milestone: Customer Accept Primo-Alma environment | 0 days | 2017-06-26 | 2017-06-26 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1 | 0% | Go-Live Milestones
| 6.1.1 | 0% | Ensure relevant jobs are enabled/disabled in preparation for go-live process | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
| 6.1.2 | 0% | Go-Live Process Run/Enabled: 1. Removes 'SCRUBBED_' from all patron and vendor emails. 2. Remove all email and ftp include list entries 3. Enable preferred term correction capability (disable_preferred_term_correction_job=false) 4. Unhide configuration (hide_configuration=false) presuming certification has been completed. 5. Enable scheduled jobs (enable_scheduled_jobs=true) | 1 hour | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Migration | ExL Imp. Updates case with Unscrub request
| 6.1.3 | 0% | Go-Live with Alma | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.4 | 0% | Go-Live with Primo-Alma | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.5 | 0% | All OpenURL compliant data sources point to Primo service page | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.6 | 0% | Complete any relevant data publish to external parties, if relevant (OCLC, Libraries Australia, COPAC, SunCat, HathiTrust, Google Scholar, among others) | .5 day | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.7 | 0% | Complete any load of local Authority records, if relevant. | .5 day | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | Customer
| 6.1.8 | 0% | Switch Customer Alma status to 'Live PS' in CRM | 0 days | 2017-06-27 | 2017-06-27 |  | Customer Contact Name | ExL Imp. Contact Name | ExL Imp.
Formulas:
Internal Use: HQ ST = Table13248[[#This Row],[Start Date/Time (Local Cust Time)]]+(O1/24)
Internal Use: HQ FT = Table13248[[#This Row],[Finish Date/ Time (Local Cust Time)]]+(O1/24)
Note on E10: Fixed duration
Note on E17: Fixed duration
Note on E18: Fixed duration
Note on E19: Fixed duration
Note on E23: Fixed duration
Note on E24: Fixed duration